# IHEP Funding Proposal Suite

Master Tracking and Submission Guide

Total Pipeline Value: $16,050,000

12 Proposals Across Federal, State, Enterprise, and Foundation Partners

Generated: December 2025

# Executive Summary

This document tracks all IHEP funding proposals, providing a comprehensive view of the funding pipeline, submission status, and strategic priorities.

## Pipeline Overview

| Category | Count | Total Value | Priority |
| --- | --- | --- | --- |

| Federal Grants | 5 | $9,050,000 | High |
| --- | --- | --- | --- |
| State/Local | 1 | $2,500,000 | High |
| Enterprise Partners | 4 | $4,100,000* | Medium |
| Foundations | 1 | $400,000 | Medium |
| Workforce | 1 | $750,000 | Medium |
| TOTAL | 12 | $16,050,000+ | - |

*Enterprise values represent projected annual contract values, not one-time grants

# Complete Proposal Inventory

## Federal Grants

| Proposal | Amount | Period | Status | Deadline |
| --- | --- | --- | --- | --- |
| NIH SBIR Phase II | $2,000,000 | 24 mo | Ready | Rolling (Apr/Aug/Dec) |
| NIMHD Health Disparities | $1,500,000 | 36 mo | Ready | Q1 2026 |
| CDC HIV Prevention | $1,200,000 | 24 mo | Ready | Q2 2026 |
| HRSA Ryan White Part F | $3,500,000 | 36 mo | Ready | Q2 2026 |
| HHS Strategic Partnership | $850,000 | 24 mo | Ready | Ongoing |

## State and Local Government

| Proposal | Amount | Period | Status | Contact |
| --- | --- | --- | --- | --- |
| Florida DOH Partnership | $2,500,000 | 36 mo | In Review | State HIV/AIDS Prog. |

## Enterprise Partnerships

| Partner | Type | Value | Status |
| --- | --- | --- | --- |
| Google Cloud Platform | Startup Program | $200K credits | Existing partnership, expansion |
| Epic Systems | App Orchard | Integration | Q1 2026 submission |
| Anthem BCBS | Value-Based Care | $150-200 PMPM | Contract discussions |
| U of Miami Miller | Research | Joint grants | IRB approved, active |

## Foundations

| Foundation | Amount | Period | Focus Area |
| --- | --- | --- | --- |
| Ford Foundation | $400,000 | 24 mo | Economic Justice |

## Workforce Development

| Program | Amount | Period | CFDA |
| --- | --- | --- | --- |
| DOL WIOA Training Grant | $750,000 | 24 mo | 17.258 |

# Recommended Submission Timeline

## Q1 2026 (January - March)

- NIH SBIR Phase II: Submit by April deadline for August review cycle

- Ford Foundation: Letter of Inquiry submission

- Google Cloud: Startup program expansion application

- Epic Systems: App Orchard application submission

## Q2 2026 (April - June)

- CDC HIV Prevention Innovation: Submit by posted deadline

- HRSA Ryan White Part F: Submit by SPNS deadline

- Ford Foundation: Full proposal (if LOI accepted)

- Anthem BCBS: Contract negotiation and signing

## Q3 2026 (July - September)

- NIMHD Health Disparities: Submit by posted deadline

- Florida DOH: Formal partnership agreement execution

- DOL WIOA: Submit to regional workforce board

## Q4 2026 (October - December)

- HHS Strategic Partnership: Initial concept meeting

- Follow-up on all pending submissions

- Prepare 2027 grant calendar

# Key Submission Resources

## Federal Grant Portals

- Grants.gov: Primary submission portal for all federal grants

- eRA Commons: NIH-specific submission and tracking

- SAM.gov: Registration required before submission (allow 2-4 weeks)

## Registration Requirements

- DUNS Number: Required for all federal applications

- SAM Registration: Must be active and current

- eRA Commons: PI account required for NIH submissions

- Grants.gov: Authorized Organizational Representative (AOR) required

## Pre-Submission Checklist

- Verify all registrations are current (SAM, Grants.gov, eRA Commons)

- Confirm funding opportunity is still open

- Review specific format requirements (page limits, fonts, margins)

- Obtain required letters of support

- Complete budget forms per agency requirements

- Internal review and sign-off from authorized official

# Generated Proposal Documents

The following proposal documents have been generated and are ready for customization:

| Document | Pages | Amount |
| --- | --- | --- |
| IHEP_NIH_SBIR_Phase_II_Proposal.docx | 12-15 | $2,000,000 |
| IHEP_NIMHD_Health_Disparities_Proposal.docx | 10-12 | $1,500,000 |
| IHEP_CDC_HIV_Prevention_Innovation_Proposal.docx | 10-12 | $1,200,000 |
| IHEP_HRSA_Ryan_White_Part_F_Proposal.docx | 12-15 | $3,500,000 |
| IHEP_HHS_Strategic_Partnership_Proposal.docx | 8-10 | $850,000 |
| IHEP_Google_Cloud_Partnership_Proposal.docx | 8-10 | $200,000 |
| IHEP_Epic_Systems_App_Orchard_Proposal.docx | 8-10 | Integration |
| IHEP_Anthem_BCBS_Value_Based_Care_Proposal.docx | 10-12 | $150-200 PMPM |
| IHEP_Florida_DOH_Statewide_Partnership_Proposal.docx | 8-10 | $2,500,000 |
| IHEP_University_of_Miami_Research_Partnership_Proposal.docx | 8-10 | Joint Grants |
| IHEP_Ford_Foundation_Economic_Justice_Proposal.docx | 8-10 | $400,000 |
| IHEP_DOL_WIOA_Workforce_Development_Proposal.docx | 10-12 | $750,000 |

## Customization Notes

Each proposal is designed as a comprehensive starting point. Before submission:

- Verify current funding opportunity announcements (FOAs) for specific requirements

- Update budget details per agency-specific forms and rates

- Add required attachments (biosketches, letters of support, etc.)

- Adjust page counts to meet specific limits

- Review and update any time-sensitive data or partnerships